MOUNT BREVITOR

ESTATE DEVELOPMENT

Residential Cluster Configuration and Revenue Projection

Workstream B  |  Document v2.0  |  March 2025  |  CONFIDENTIAL

Developer: Infinity Developers Inc (Ltd, Barbados)

# 1. Cluster Configuration

The 355 residential units are organised into five clusters, each targeting a specific market segment and product type. Clusters are phased to front-load affordable and mid-range product (where demand is strongest and most evidenced) and defer upper-tier product until market data from earlier phases confirms willingness to pay.

| Cluster | Acres | Units | Product | Target Buyer | Density |
| --- | --- | --- | --- | --- | --- |
| A - Entry/Mid | 12-14 | 100-110 | 1-bed condos, 2-bed townhouses | Local Barbadian first-time buyers, regional investors | 7-8 units/acre |
| B - Mid-Range | 12-14 | 90-100 | 2-bed and 3-bed townhouses | Local upgraders, diaspora return buyers | 6-7 units/acre |
| C - Mid-Upper | 10-12 | 70-80 | 3-bed townhouses, some 4-bed | Established families, diaspora, international | 6-7 units/acre |
| D - Upper | 10-12 | 45-55 | 4-bed homes, bungalows | Upper-income local, international lifestyle buyers | 4-5 units/acre |
| E - Premium | 10-12 | 30-40 | 5-bed estate homes | International, diaspora, HNW local | 3-4 units/acre |
| TOTAL | 55-60 | 355 |  |  | ~6 avg |

Cluster A and B (entry and mid-range) account for 190-210 units, or 54-59% of total supply. These clusters target the strongest demand segment (local Barbadian buyers, BBD 440,000 to BBD 623,700) and are released in Phases 1 and 2 to generate early revenue and establish the estate.

Clusters D and E (upper and premium) account for 75-95 units, or 21-27% of total supply. These are deferred to Phases 3 and 4.

FLAG: Upper-tier pricing (USD 440,000 to USD 715,000 for 4-5 bed homes) is above documented mid-market comparables in northern Barbados. Demand at this level is unverified. Do not commit Cluster D and E construction capital until Phase 2 absorption data confirms buyer willingness to pay above USD 350,000.

# 2. Unit Mix and Pricing Matrix

| Type | Beds | Size (sq ft) | Units | Price BBD | Price USD | Phase | Cluster | Gross Rev BBD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Condo | 1 | 600-700 | 80 | 440,000 | 220,000 | 1-2 | A | 35,200,000 |
| Townhouse | 2 | 850-950 | 95 | 560,000 | 280,000 | 1-2 | A/B | 53,200,000 |
| Townhouse | 3 | 1,100-1,200 | 85 | 623,700 | 311,850 | 2-3 | B/C | 53,014,500 |
| Bungalow/Home | 4 | 1,500-1,800 | 55 | 880,000 | 440,000 | 3-4 | D | 48,400,000 |
| Estate Home | 5 | 2,200-2,800 | 40 | 1,430,000 | 715,000 | 3-4 | E | 57,200,000 |
| TOTAL |  |  | 355 |  |  | 1-4 | A-E | 247,014,500 |

Total gross residential revenue: BBD 247,014,500 (USD 123,507,250). This is residential sales only and excludes non-residential revenue streams (farm, golf, commercial, solar, amenity fees).

# 3. Revenue Projection by Phase

| Phase | Period | Units | Revenue BBD | Revenue USD | Cum. Units | Cum. Rev BBD |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Q3 2025 - Q2 2026 | 80-90 | 42,600,000 | 21,300,000 | 80-90 | 42,600,000 |
| 2 | Q3 2026 - Q2 2027 | 100-120 | 65,500,000 | 32,750,000 | 180-210 | 108,100,000 |
| 3 | Q3 2027 - Q2 2028 | 85-100 | 68,200,000 | 34,100,000 | 265-310 | 176,300,000 |
| 4 | Q3 2028 - Q4 2028 | 45-55 | 70,714,500 | 35,357,250 | 355 | 247,014,500 |
| TOTAL | 2025-2028 | 355 | 247,014,500 | 123,507,250 |  |  |

Revenue concentration: Phases 2 and 3 account for approximately 54% of total residential revenue. This is the period of peak capital deployment and maximum construction activity. Cash flow management during this period is critical.

Phase 4 revenue is disproportionately high relative to unit count because it includes the premium 5-bed estate homes at BBD 1,430,000 each. This revenue is at risk if upper-tier demand does not materialise.

# 4. Comparable Pricing Validation

Mount Brevitor pricing has been benchmarked against four comparable developments identified in Phase 1. Current pricing is sourced from developer websites and Terra Caribbean listings as of March 2025.

| Development | Price Range USD | $/sq ft (est.) | Location | Source / Notes |
| --- | --- | --- | --- | --- |
| Coverley Residences | 303K-429K | 220-240 | Christ Church | Developer website / Terra Caribbean. Town centre, community amenities. |
| Vuemont Country Estate | 275K-355K | 200-230 | St. Peter | Developer website. Same parish as Mount Brevitor. Pool, gym, trails. |
| Harmony Estates | 150K base | 150-190 | Christ Church | Developer website. Affordable segment. 100% financing. Below MBE entry. |
| Apes Hill | 500K+ | 300+ | St. James | Developer website. Luxury benchmark. Golf, farm-to-table, spa. |
| Mount Brevitor (proposed) | 220K-715K | 230-350 (est.) | St. Peter (TBC) | Developer pricing. Entry competitive. Upper-tier unvalidated. |

Entry and mid-range pricing (USD 220K to USD 350K) is competitive with Coverley and Vuemont. The 1-bed condo at USD 220K undercuts Coverley's entry point, which is strategically sound for market penetration. The 95% financing product further strengthens the value proposition for the entry segment.

FLAG: Upper-tier pricing (USD 440K to USD 715K) overlaps with the lower end of the Apes Hill luxury segment. Apes Hill offers an established 18-hole golf course, plantation setting, spa, and beach club. Mount Brevitor's amenity package is differentiated (farm, X Range, community services) but is unproven at this price point in northern Barbados. Independent luxury market validation is outstanding.

# 5. Absorption Rate Model

Three absorption scenarios are modelled, consistent with the Phase 1 Residential Demand Analysis. The developer's financial model aligns with the Base Case to Optimistic range.

| Scenario | Annual Rate | Sellout | Assumptions |
| --- | --- | --- | --- |
| Conservative | 60-80 units/yr | 4.5-6 years | Local demand only. No diaspora or international premium. Pricing under pressure from competition. |
| Base Case | 100-120 units/yr | 3-3.5 years | Local demand + diaspora. Financing innovation works. Amenity package supports pricing. |
| Optimistic | 130-150 units/yr | 2.5-3 years | Strong demand across all segments. Northern Barbados growth accelerates. Upper-tier absorbs. |

Market precedent: Harmony Estates sold 96 units in under two years (approximately 50 units per year). Coverley has sustained multi-phase absorption at a larger scale. The Base Case assumption of 100-120 units per year is achievable but at the upper end of Barbados market precedent for a single development.

Key absorption dependencies: the 95% mortgage product must be operational at launch; the amenity package (farm, golf, community services) must be visible and credible to buyers by Phase 2; and competing supply (Coverley Phase 2, Vuemont expansion) must not accelerate into the same segment simultaneously.

# 6. Sales and Marketing Strategy Brief

## 6.1 Target Markets and Channels

- Local Barbadian (55-65%): on-island real estate agents, social media (Facebook, Instagram), newspaper advertising, radio. Model home tours. Bank partnership marketing through mortgage pre-approval events.

- Barbadian Diaspora (15-20%): UK and North American Caribbean media. Diaspora community events and organisations. Digital marketing targeting Barbadian nationals abroad. Virtual tours and off-plan purchase facilitation.

- International / Remote Worker (10-15%): Barbados Welcome Stamp programme channels. International property platforms (Rightmove International, Realtor.com International). Lifestyle media targeting remote workers and early retirees.

- Regional Investor (5-10%): Caribbean investment forums. Regional banking and wealth management channels. Property investment conferences in Trinidad and Jamaica.

## 6.2 Pricing Approach

Launch pricing at the lower end of the range for Phase 1 units. Apply a 3-5% price escalation per phase, benchmarked against market movement and absorption data. The 95% financing product is the primary demand driver for the local segment; all sales materials should lead with the deposit amount (BBD 22,000 / USD 11,000) rather than the unit price.

## 6.3 Pre-Sales Strategy

The developer targets a pre-sales threshold of 10% (approximately 35 units) before committing Phase 1 construction capital. This is below the industry norm of 20-30% for developments of this scale. A higher pre-sales threshold is recommended (20%, or approximately 70 units) to reduce demand risk and satisfy lender requirements.

FLAG: A 10% pre-sales threshold exposes the project to construction commencement with limited demand evidence. This is a material risk for the financing structure and was flagged as Risk M-03 in the Phase 1 Risk Register. Recommend increasing to 20% minimum.

## 6.4 Financing Model

The 95% LTV mortgage at 4.5% fixed for 25 years is the cornerstone of the sales strategy for the local market. Key metrics:

- Entry unit (BBD 440,000): Deposit BBD 22,000 (USD 11,000). Monthly payment approximately BBD 2,310 (USD 1,155).

- Mid-range unit (BBD 623,700): Deposit BBD 31,185 (USD 15,593). Monthly payment approximately BBD 3,275 (USD 1,638).

- Qualification: a household earning BBD 80,000 per year (approximately USD 40,000) could service the entry unit mortgage, assuming a 35% debt-to-income ratio. This is within the middle-income Barbadian salary band.

FLAG: The 4.5% fixed rate is below Barbados commercial mortgage rates (typically 6-8%). The banking partnership and rate basis must be confirmed by the developer. If the rate is subsidised or introductory, the effective buyer cost may be higher than presented.

End of Document

Mount Brevitor Estate Development  |  Residential Configuration v2.0  |  Infinity Developers Inc  |  Confidential