## Risk Register
MOUNT BREVITOR ESTATE DEVELOPMENT
Project Risk Register ¦ Workstream F ¦ v2.0 ¦ March 2025 ¦ CONFIDENTIAL
Prepared by: Strategic Advisory Workstream ¦ Developer: Infinity Developers Inc ¦ Currency: BBD / USD (BBD 2.00 = USD 1.00)
Ref | Risk Category | Risk Description | Likelihood | Impact | Risk Rating | Workstream Affected | Mitigation Action | Owner | Mitigation Status | Target Date | Source
PLANNING AND REGULATORY
P-01 | Planning | Agricultural land conversion for the 6-acre parcel is refused or subject to conditions that prevent X Range and solar installation. This is the critical path item for planning. | Medium | High | HIGH | Planning, Golf, Energy | Initiate pre-application meeting with TCPD and Ministry of Agriculture immediately. Prepare agricultural impact assessment. Identify fallback location for X Range if conversion is refused. | Developer / Legal Counsel | Not Started | Q2 2025 | Phase 1
P-02 | Planning | Parish and exact site zoning classification remain unconfirmed. If the site falls within or adjacent to a Special Development Area (CAP237A), additional consents and restrictions apply. | Medium | High | HIGH | Planning, All Workstreams | Confirm parish via title search. Obtain Physical Development Plan zone map extract from TCPD. Check SDA boundary maps against site coordinates. | Developer / Legal Counsel | Not Started | Q2 2025 | Phase 1
P-03 | Planning | Environmental Impact Assessment (EIA) is triggered under 2021 Regulations. Mandatory EIA for 120-acre mixed-use development is almost certain. EIA preparation and approval may take 6-12 months. | High | Medium | HIGH | Planning, Timeline | Engage environmental consultant immediately. Begin baseline studies (ecology, hydrology, noise) in parallel with planning pre-application to compress timeline. | Developer / Environmental Consultant | Not Started | Q2 2025 | Phase 1
P-04 | Planning | Planning permission is refused or subject to material conditions by TCPD, delaying or constraining the development programme. | Medium | High | HIGH | All Workstreams | File pre-application with TCPD to test appetite. Design scheme to align with Physical Development Plan objectives. Engage planning counsel early. | Developer / Planning Counsel | Not Started | Q2 2025 | Phase 1
P-05 | Planning | Tourism Development Act classification is applied to X Range, triggering additional Tourism Development Corporation approval and conditions. | Medium | Low | MEDIUM | Golf, Planning | Seek preliminary classification guidance from Tourism Development Corporation before submitting planning application. | Developer / Legal Counsel | Not Started | Q3 2025 | Phase 1
P-06 | Planning | Water treatment and electrical generation consents from BWA and BL&P/FTC are delayed or conditional, affecting infrastructure delivery schedule. | Low | Medium | MEDIUM | Infrastructure, Timeline | Submit utility applications in parallel with planning. Maintain BWA and BL&P engagement from pre-application stage. | Developer / Engineers | Not Started | Q3 2025 | Phase 1
P-07 | Planning | EDGE or LEED certification requirements impose design constraints or additional costs not currently reflected in the development budget. Certification pathway identified in Phase 2 Environmental Brief. | Low | Medium | MEDIUM | Design, Sustainability | Confirm certification target at design stage. Integrate certification requirements into architectural brief before construction tender. | Developer / Design Team | Not Started | Q3 2025 | Phase 2 - Environmental Brief
FINANCIAL
F-01 | Financial | USD 57M facility at 5% interest is below Barbados commercial market rates (6-9%). If the facility is commercial rather than strategic, interest cost is materially understated, compressing net profit. | High | High | CRITICAL | Financial Model, Investor Presentation | Developer to confirm lender type and rate basis. Model sensitivity at 6%, 7%, and 8% interest rates. Disclose rate assumption in all investor materials. | Developer / CFO | Not Started | Immediate | Phase 1
F-02 | Financial | Construction cost savings of 20-30% from proprietary technology are not independently verified. If actual costs track BCQS 2025 benchmarks (USD 140-180/sq ft modest), the 45% margin target compresses materially. | Medium | High | HIGH | Financial Model, Development Appraisal | Require independent cost verification or third-party quantity surveyor estimate. Model base case at BCQS benchmark costs as a downside scenario. | Developer / QS | In Progress | Q2 2025 | Phase 1
F-03 | Financial | Pre-sales assumption of 10% before construction commencement is below industry norm of 20-30%. If sales lag, the project is under-collateralised at construction start. | Medium | High | HIGH | Financial Model, Sales Strategy | Revise pre-sales threshold to minimum 20%. Structure marketing launch 6 months ahead of construction. Secure reservation agreements before committing construction draws. | Developer / Sales | Not Started | Q2 2025 | Phase 1
F-04 | Financial | Peak capital requirement exceeds draw schedule. The 2026 draw of approximately USD 39M is the heaviest year. Any cost overrun or revenue delay concentrates cash pressure. | Medium | High | HIGH | Financial Model, Cash Flow | Build 10-15% contingency into draw schedule. Maintain minimum 3-month liquidity buffer. Structure draw schedule with milestone-gated releases. | Developer / CFO | Not Started | Q2 2025 | Phase 1
F-05 | Financial | Currency risk: all financing and significant cost items are in USD; residential sales are in BBD. BBD peg to USD (2:1) is fixed but sovereign risk remains. | Low | Medium | MEDIUM | Financial Model | Monitor Barbados sovereign credit and IMF programme compliance. BBD peg has held since 1975. Low probability but high impact if peg is adjusted. | Developer / Advisory | Ongoing | Ongoing | Phase 1
F-06 | Financial | Development entity ownership structure is TBD. Delays in structuring the SPV or holding company could impede loan drawdown, land transfer, or investor onboarding. | Medium | Medium | MEDIUM | Legal Structure, Capital Raising | Engage corporate counsel to establish SPV structure before first draw. Confirm tax, liability, and equity allocation arrangements. | Developer / Legal Counsel | Not Started | Q2 2025 | Phase 1
F-07 | Financial | Seller-side transaction taxes (property transfer tax 2.5% plus stamp duty 1.0% = 3.5%) on projected gross revenue of BBD 198.3M represent approximately BBD 6.9M (USD 3.5M) in costs. If not modelled as cost of sale, net profit is overstated. | Medium | High | HIGH | Financial Model, Legal Structure | Confirm 3.5% seller-side transfer cost is included in the development appraisal as a cost of sale. Verify treatment in all investor materials. | Developer / CFO | Identified | Q2 2025 | Phase 2 - Legal Note
F-08 | Financial | Corporation tax rate of 9% (2024 amendment) replaces the previous tiered structure. If the financial model uses the old tiered rates, taxable profit and investor returns are overstated. | Medium | Medium | MEDIUM | Financial Model, Tax | Confirm the financial model reflects the 9% corporation tax rate. Engage Barbados tax counsel to confirm effective rate and any available reliefs. | Developer / Tax Advisor | Identified | Q2 2025 | Phase 2 - Legal Note
F-09 | Financial | VAT at 17.5% applies to construction services and professional fees. Input VAT recovery on commercial components (X Range, retail) must be structured correctly to avoid irrecoverable VAT leakage. | Low | Medium | MEDIUM | Financial Model, Tax | Engage VAT specialist to confirm input VAT recovery entitlement on commercial vs. residential components. Register SPV for VAT before construction commences. | Developer / Tax Advisor | Not Started | Q3 2025 | Phase 2 - Legal Note
MARKET
M-01 | Market | Upper-tier pricing (USD 500K-715K) is above documented Barbados mid-market comparables. Absorption at this level is unverified for northern Barbados. Luxury market validation is outstanding. | Medium | High | HIGH | Residential, Financial Model | Commission independent luxury market study for northern Barbados. Identify comparable luxury sales in St. Peter/St. James. Defer upper-tier launch until demand evidence supports pricing. | Developer / Sales | Not Started | Q2 2025 | Phase 1
M-02 | Market | 355 units is a large programme for Barbados. Annual absorption of 100-150 units per year is at the upper end of market precedent. A softening in demand or competing supply could slow sales. | Medium | Medium | MEDIUM | Residential, Phasing | Phase releases in tranches of 50-80 units. Monitor absorption quarterly. Adjust phasing and pricing dynamically. Maintain optionality on later phases. | Developer / Sales | Not Started | Q2 2025 | Phase 1
M-03 | Market | Competing developments (Coverley Phase 2, Vuemont expansion, Indigo) deliver additional supply into the same market segment, increasing competition for the middle-income buyer. | Medium | Medium | MEDIUM | Residential, Pricing | Differentiate on estate identity (farm, golf, green credentials, community). Monitor competing supply pipeline quarterly. Price competitively at launch. | Developer / Marketing | Not Started | Ongoing | Phase 1
M-04 | Market | Diaspora and international buyer demand is assumed but not validated through structured research. If this segment underperforms, the project is reliant on local demand alone. | Medium | Medium | MEDIUM | Residential, Sales Strategy | Conduct targeted outreach to UK and North American Barbadian diaspora. Commission buyer sentiment survey. Build international marketing channel. | Developer / Marketing | Not Started | Q3 2025 | Phase 1
M-05 | Market | Interest rate increases by Barbados commercial banks reduce mortgage affordability for target buyers. Developer-offered 4.5% fixed rate depends on bank partnership terms holding. | Low | Medium | MEDIUM | Residential, Sales | Secure written confirmation of mortgage product terms from partner banks. Build interest rate sensitivity into buyer affordability models. | Developer / Banking Partners | Not Started | Q2 2025 | Phase 1
M-06 | Market | Brand positioning relies on five pillars (farm, golf, sustainability, community, location) that require visible delivery to sustain pricing premium. If amenity delivery lags residential sales, buyer confidence erodes. | Medium | Medium | MEDIUM | Brand, Sales, Construction | Sequence amenity delivery (farm operations, X Range, community facilities) ahead of or concurrent with Phase 2 residential handover. Budget for early amenity activation. | Developer / Marketing | Identified | Q3 2025 | Phase 2 - Brand Document
CONSTRUCTION
C-01 | Construction | Site topography, geotechnical conditions, and soil characteristics are not fully surveyed. Northern Barbados terrain is undulating. Unforeseen ground conditions could increase site preparation costs above USD 20,000/acre estimate. | Medium | Medium | MEDIUM | Construction, Financial Model | Commission topography and geotechnical survey before detailed design. Include 15% site preparation contingency in cost model. | Developer / Engineers | Not Started | Q2 2025 | Phase 1
C-02 | Construction | Construction cost escalation exceeds the 4.3% annual rate (BCQS 2025). Materials supply chain disruption, labour shortages, or import cost increases drive costs above budget. | Medium | Medium | MEDIUM | Construction, Financial Model | Fix material prices through early procurement contracts where possible. Include escalation allowance in the development appraisal. Monitor BCQS quarterly updates. | Developer / Contractor | Ongoing | Ongoing | Phase 1
C-03 | Construction | Proprietary building technology fails to deliver claimed speed and cost advantages during construction. Delivery timeline and cost model are both affected. | Medium | High | HIGH | Construction, Financial Model, Timeline | Require technology pilot on model home build (Q4 2025). If pilot underperforms, revert to conventional construction cost and timeline assumptions. | Developer / Construction Manager | Not Started | Q4 2025 | Phase 1
C-04 | Construction | Contractor and skilled labour availability in northern Barbados is insufficient for 355-unit programme. Local construction workforce is limited; large projects compete for the same pool. | Medium | Medium | MEDIUM | Construction, Timeline | Pre-qualify contractors early. Consider phased contractor engagement. Evaluate importing specialist labour if needed, subject to work permit requirements. | Developer / Procurement | Not Started | Q3 2025 | Phase 1
C-05 | Construction | Infrastructure delivery (roads, water, sewage, electrical) is delayed, preventing residential handover despite units being complete. | Medium | High | HIGH | Infrastructure, Sales, Timeline | Sequence infrastructure works ahead of unit completion. Include infrastructure milestones in draw schedule. Require infrastructure completion certificates before unit marketing as ready to occupy. | Developer / Engineers | Not Started | Q3 2025 | Phase 1
OPERATIONAL
O-01 | Operational | Farm business model has not been selected. Without a confirmed model, farm capex, revenue projections, and operational planning cannot be finalised. Developer model assumes USD 2M setup and USD 1.5-1.8M annual revenue from Year 3. | Medium | Medium | MEDIUM | Agri-Estate, Financial Model | Complete farm business model scoring. Select model or combination. Validate capex and revenue assumptions against selected model. | Advisory / Developer | In Progress | Q2 2025 | Phase 1
O-02 | Operational | X Range format, footprint, capex, and operator model are not documented. The golf entertainment workstream cannot be financially modelled until these are confirmed. | High | High | CRITICAL | Golf, Financial Model, Land Allocation | Developer to provide X Range brand specifications, operator agreement, and capex estimate. Engage X Range operator for term sheet. | Developer | In Progress | Q2 2025 | Phase 1
O-03 | Operational | Medical centre and supermarket are phased from Phase 2 but require minimum resident population to be commercially viable. Early delivery without residents creates operating losses. | Low | Medium | MEDIUM | Community Infrastructure, Phasing | Tie medical centre and supermarket delivery to residential absorption milestones (minimum 100 occupied units). Identify interim operator or anchor tenant. | Developer / Operations | Not Started | Q4 2025 | Phase 1
O-04 | Operational | On-site water treatment plant and hybrid energy system require ongoing maintenance, specialist staffing, and regulatory compliance. Operating costs may exceed initial estimates. | Low | Medium | MEDIUM | Infrastructure, Operating Costs | Engage utility management contractor. Build maintenance reserve into operating budget. Ensure regulatory compliance schedule is established at commissioning. | Developer / Facilities | Not Started | Q1 2026 | Phase 1
O-05 | Operational | X Range revenue model (base case BBD 2.8M/year) depends on resident, visitor, and corporate demand materialising across three market segments simultaneously. If resident population builds slowly, early-year revenue underperforms. | Medium | Medium | MEDIUM | Golf, Financial Model | Phase X Range launch to coincide with minimum 80 occupied units. Build conservative ramp-up (50% of base case in Year 1) into operating model. | Developer / X Range Operator | Identified | Q3 2025 | Phase 2 - X Range Brief
O-06 | Operational | Estate management body (HOA or management company) is not yet structured. Without a credible management entity, common area maintenance, amenity operations, and service charge collection are at risk. | Medium | Medium | MEDIUM | Operations, Legal, Sales | Draft HOA or estate management framework before first unit sale. Define service charge structure and management responsibilities in the sales agreement. | Developer / Legal Counsel | Not Started | Q3 2025 | Phase 2 - Legal Note
ENVIRONMENTAL
E-01 | Environmental | EIA identifies environmental sensitivities (protected species, water table, coastal impact) that require design modifications or restrict development on parts of the site. | Medium | Medium | MEDIUM | Planning, Design, Land Allocation | Commission EIA early. Incorporate baseline studies into design from the start. Maintain design flexibility on environmentally sensitive areas. | Developer / Environmental Consultant | Not Started | Q2 2025 | Phase 1
E-02 | Environmental | Green certification target (EDGE Advanced or LEED Silver) is not achieved, undermining marketing positioning and potential investor/buyer expectations. | Low | Medium | MEDIUM | Design, Marketing, Sales | Confirm certification target and engage certification consultant at design stage. Build certification requirements into architectural brief and contractor specifications. | Developer / Design Team | Not Started | Q3 2025 | Phase 1
E-03 | Environmental | Climate risk: northern Barbados is exposed to hurricane and tropical storm events. Storm damage during construction or post-completion could cause material loss and insurance claims. | Medium | High | HIGH | Construction, Insurance, Operations | Design to Barbados Building Code wind load standards. Procure comprehensive construction-phase and operational insurance including hurricane cover. Include construction weather downtime in schedule. | Developer / Insurance Broker | Not Started | Q3 2025 | Phase 1
E-04 | Environmental | Agrivoltaic solar installation on agricultural land faces scrutiny for environmental and agricultural impact. Dual-use approval may require demonstration of continued agricultural productivity. | Medium | Medium | MEDIUM | Energy, Farm, Planning | Prepare agrivoltaic impact study demonstrating continued agricultural output under solar canopy. Engage Ministry of Agriculture early on dual-use design. | Developer / Energy Consultant | Not Started | Q3 2025 | Phase 1
E-05 | Environmental | Carbon and energy modelling indicates the estate generates approximately 2,840 tCO2e annually under the baseline scenario. Without the 1.2 MW solar array, the estate cannot credibly claim carbon reduction, weakening sustainability positioning. | Medium | Medium | MEDIUM | Energy, Sustainability, Marketing | Confirm solar array as a Phase 1 infrastructure priority. Model net carbon position with and without solar. Do not market carbon claims until solar is commissioned. | Developer / Energy Consultant | Identified | Q3 2025 | Phase 2 - Environmental Brief
E-06 | Environmental | Water demand of approximately 233,000 gallons per day (residential, farm, amenities combined) exceeds typical northern Barbados supply capacity. On-site treatment plant must be commissioned before Phase 2 occupancy. | Medium | High | HIGH | Infrastructure, Planning | Confirm BWA supply capacity for Phase 1. Design on-site treatment plant to meet Phase 2+ demand. Include water stress contingency in infrastructure budget. | Developer / Engineers | Identified | Q2 2025 | Phase 2 - Environmental Brief
TIMELINE
T-01 | Timeline | 2025 P&L assumes USD 15.2M revenue from lot sales beginning September 2025. This requires land purchase, planning, and lot release within approximately 6 months, an aggressive timeline for Barbados. | High | Medium | HIGH | Financial Model, Cash Flow | Stress-test cash flow with 6-month and 12-month revenue delay scenarios. Do not commit construction draws until pre-sales are secured. | Developer / CFO | Not Started | Immediate | Phase 1
T-02 | Timeline | 48-month development cycle for 355+ units on greenfield is aggressive. Any planning delay, construction slippage, or sales lag extends the programme and increases financing costs. | Medium | Medium | MEDIUM | All Workstreams | Build 6-month buffer into overall programme. Phase milestones with go/no-go decision points. Monitor monthly against programme. | Developer / Project Manager | Not Started | Ongoing | Phase 1
T-03 | Timeline | Planning timeline (12-18 months from pre-application to first building permit) is materially longer than the developer's financial model assumes. Revenue commencement date is at risk of 6-12 month delay. | High | High | CRITICAL | Financial Model, Planning, Cash Flow | Revise the financial model to reflect a realistic 12-18 month planning timeline. Do not commit construction capital until planning status provides confidence. Stress-test cash flow with delayed revenue. | Developer / CFO | Identified | Immediate | Phase 2 - Planning Analysis
LEGAL AND STRUCTURAL
L-01 | Legal | SPV has not been incorporated. Without the SPV, land acquisition cannot close in the project entity, investor onboarding is blocked, and loan documentation cannot be executed. | High | High | CRITICAL | Legal, Capital Raising, All Workstreams | Incorporate the SPV (Mount Brevitor Development Ltd or equivalent) before the first capital raise or land acquisition closing. Engage CAIPO for registration. | Developer / Legal Counsel | Not Started | Immediate | Phase 2 - Legal Note
L-02 | Legal | Beneficial ownership disclosure requirements are not yet addressed. Non-compliance exposes the SPV to regulatory risk and may impede bank account opening and ECA registration. | Medium | Medium | MEDIUM | Legal, Compliance | Establish beneficial ownership register at the registered office upon incorporation. Identify all natural persons holding 25% or more of shares or voting rights. | Developer / Company Secretary | Not Started | Q2 2025 | Phase 2 - Legal Note
L-03 | Legal | Non-resident investors who fail to register foreign currency with the Exchange Control Authority at the time of investment may permanently lose the right to repatriate capital and profits. | Medium | High | HIGH | Legal, Capital Raising | Build ECA registration into the investor onboarding process. Legal counsel to manage registration for each non-resident investor before or at the time of remittance. | Developer / Legal Counsel | Not Started | Q2 2025 | Phase 2 - Legal Note
L-04 | Legal | JV structure (if pursued) introduces deadlock risk, shared control, and complex exit mechanics. A poorly drafted JV agreement could paralyse decision-making during construction. | Medium | High | HIGH | Legal, Governance | Decide on JV vs. passive investor structure before capital raise. If JV is pursued, negotiate heads of terms before engaging counsel. Include deadlock resolution (shotgun clause or buy/sell). | Developer / Legal Counsel | Not Started | Q2 2025 | Phase 2 - Legal Note

## Risk Summary
RISK SUMMARY
v2.0 ¦ March 2025 ¦ CONFIDENTIAL
Risk Rating | Phase 1 Count | Phase 2 New | Total Count | References
CRITICAL | 2 | 2 | 4 | F-01, O-02, T-03, L-01
HIGH | 12 | 4 | 16 | P-01, P-02, P-03, P-04, F-02, F-03, F-04, F-07, M-01, C-03, C-05, E-03, E-06, T-01, L-03, L-04
MEDIUM | 18 | 8 | 26 | P-05, P-06, P-07, F-05, F-06, F-08, F-09, M-02, M-03, M-04, M-05, M-06, C-01, C-02, C-04, O-01, O-03, O-04, O-05, O-06, E-01, E-02, E-04, E-05, T-02, L-02
LOW | 0 | 0 | 0
TOTAL | 32 | 14 | 46
Methodology: Risks identified from Phase 1 Strategic Master Analysis v1.0, Phase 2 Investment Suite analysis (Financial Model, Legal Structure Note, Environmental Brief, X Range Brief, Brand Positioning, Land Allocation Strategy), confirmed parameters, open items register, regulatory file set, and developer financial model. Likelihood and Impact assessed on a High/Medium/Low scale. Risk Rating is the combined assessment: CRITICAL (requires immediate resolution), HIGH (material impact, active mitigation required), MEDIUM (manageable with standard controls), LOW (monitor only).

## Mitigation Tracker
MITIGATION STATUS TRACKER
v2.0 ¦ March 2025 ¦ CONFIDENTIAL
Ref | Risk Rating | Short Description | Mitigation Status | Owner | Target Date | Next Action
P-01 | HIGH | Agricultural land conversion for the 6-acre parcel is refused or subject to conditions that prevent ... | Not Started | Developer / Legal Counsel | Q2 2025 | Initiate pre-application meeting with TCPD and Ministry of Agriculture immediately.
P-02 | HIGH | Parish and exact site zoning classification remain unconfirmed. If the site falls within or adjacent... | Not Started | Developer / Legal Counsel | Q2 2025 | Confirm parish via title search.
P-03 | HIGH | Environmental Impact Assessment (EIA) is triggered under 2021 Regulations. Mandatory EIA for 120-acr... | Not Started | Developer / Environmental Consultant | Q2 2025 | Engage environmental consultant immediately.
P-04 | HIGH | Planning permission is refused or subject to material conditions by TCPD, delaying or constraining t... | Not Started | Developer / Planning Counsel | Q2 2025 | File pre-application with TCPD to test appetite.
F-01 | CRITICAL | USD 57M facility at 5% interest is below Barbados commercial market rates (6-9%). If the facility is... | Not Started | Developer / CFO | Immediate | Developer to confirm lender type and rate basis.
F-02 | HIGH | Construction cost savings of 20-30% from proprietary technology are not independently verified. If a... | In Progress | Developer / QS | Q2 2025 | Require independent cost verification or third-party quantity surveyor estimate.
F-03 | HIGH | Pre-sales assumption of 10% before construction commencement is below industry norm of 20-30%. If sa... | Not Started | Developer / Sales | Q2 2025 | Revise pre-sales threshold to minimum 20%.
F-04 | HIGH | Peak capital requirement exceeds draw schedule. The 2026 draw of approximately USD 39M is the heavie... | Not Started | Developer / CFO | Q2 2025 | Build 10-15% contingency into draw schedule.
F-07 | HIGH | Seller-side transaction taxes (property transfer tax 2.5% plus stamp duty 1.0% = 3.5%) on projected ... | Identified | Developer / CFO | Q2 2025 | Confirm 3.
M-01 | HIGH | Upper-tier pricing (USD 500K-715K) is above documented Barbados mid-market comparables. Absorption a... | Not Started | Developer / Sales | Q2 2025 | Commission independent luxury market study for northern Barbados.
C-03 | HIGH | Proprietary building technology fails to deliver claimed speed and cost advantages during constructi... | Not Started | Developer / Construction Manager | Q4 2025 | Require technology pilot on model home build (Q4 2025).
C-05 | HIGH | Infrastructure delivery (roads, water, sewage, electrical) is delayed, preventing residential handov... | Not Started | Developer / Engineers | Q3 2025 | Sequence infrastructure works ahead of unit completion.
O-02 | CRITICAL | X Range format, footprint, capex, and operator model are not documented. The golf entertainment work... | In Progress | Developer | Q2 2025 | Developer to provide X Range brand specifications, operator agreement, and capex estimate.
E-03 | HIGH | Climate risk: northern Barbados is exposed to hurricane and tropical storm events. Storm damage duri... | Not Started | Developer / Insurance Broker | Q3 2025 | Design to Barbados Building Code wind load standards.
E-06 | HIGH | Water demand of approximately 233,000 gallons per day (residential, farm, amenities combined) exceed... | Identified | Developer / Engineers | Q2 2025 | Confirm BWA supply capacity for Phase 1.
T-01 | HIGH | 2025 P&L assumes USD 15.2M revenue from lot sales beginning September 2025. This requires land purch... | Not Started | Developer / CFO | Immediate | Stress-test cash flow with 6-month and 12-month revenue delay scenarios.
T-03 | CRITICAL | Planning timeline (12-18 months from pre-application to first building permit) is materially longer ... | Identified | Developer / CFO | Immediate | Revise the financial model to reflect a realistic 12-18 month planning timeline.
L-01 | CRITICAL | SPV has not been incorporated. Without the SPV, land acquisition cannot close in the project entity,... | Not Started | Developer / Legal Counsel | Immediate | Incorporate the SPV (Mount Brevitor Development Ltd or equivalent) before the first capital raise or land acquisition closing.
L-03 | HIGH | Non-resident investors who fail to register foreign currency with the Exchange Control Authority at ... | Not Started | Developer / Legal Counsel | Q2 2025 | Build ECA registration into the investor onboarding process.
L-04 | HIGH | JV structure (if pursued) introduces deadlock risk, shared control, and complex exit mechanics. A po... | Not Started | Developer / Legal Counsel | Q2 2025 | Decide on JV vs.